## Task List
ICICI BANK - ZSCALER IMPLEMENTATION TASK LIST
Task Completed By -
Date | Sl No | Task Assigned | Manjunath | Tausif | Priyanka | Karuna | Trupti | Remarks
7th April 2022 | 1 | Block Chat, Post, Like, Comment for Facebook, Twitter, Linkedin & Instagram. | Post, Like- FB & TW | Post, Like, Comment - LinkedIn | Post, Like - Insta | Post, Like, Comment - LinkedIn | Comment & Post - FB
| 2 | Only one youtube channel should be allowed https://m.youtube.com/user/icicibank | Done | Done | Done | Done | Done
| 3 | In Linkedin test case, linkedin.com should be accessible but cannot upload/download or comment. | Done | Done | Done | Done | Done
8th April 2022 | 4 | Create a policy for web search category ssl interception & update if google.com and bing.com ssl interception from the browser. | Done | Done | Done | Done | Done
9th April 2022 | 5 | Re- direct Instagram, LinkedIn and Twitter to Meta respective pages
11th April 2022 | 6 | Create a policy in Zscaler to block uploads to all the websites, Test it and confirm if this can be achivbable. | Done | Done | Done | Done | Done